## Feuille1
Catégorie	Type	Nom tâche	Temps estimé	Temps passé	Temps restant	Avancement
réflexion		bien comprendre le sujet		01:08:00	00:00:00	1
base	conception	conception MCD	01:00:00	01:00:00	00:00:00	1
base	sql	Base avec MPD avec toutes les contraintes et enum	00:15:00	00:15:00	00:00:00	1
base	test	insertion des données de test	00:30:00	00:30:00	00:00:00	1
Global	correction	Correction à faire	01:00:00	01:30:00	00:00:00	1
Affichage	orthographe	orthographe de l’affichage	00:30:00	00:30:00	00:00:00	1
Global	base	BaseModel	00:05:00	00:05:00	00:00:00	1
Page Utilisateur	CRUD	Faire le CRUD	00:10:00	00:15:00	00:00:00	1
Page Categorie	CRUD	Faire le CRUD	00:30:00	00:45:00	00:00:00	1
Page Employé	CRUD	Faire le CRUD	00:30:00	00:45:00	00:00:00	1
Page Suppl	CRUD	Faire le CRUD	00:30:00	00:38:00	00:00:00	1
Page pointage	affichage	liste employés	00:05:00	00:05:00	00:00:00	1
Page pointage	contrôlleur	GetEmploye & GetPointage	00:05:00	00:09:00	00:00:00	1
Page pointage	affichage	Pointage	00:20:00	00:27:00	00:00:00	1
Page pointage	contrôlleur	postPointage	00:05:00	00:10:00	00:00:00	1
Page pointage	métier	calculerHeure	01:00:00	01:29:00	00:00:00	1
Page max supp	CRUD	Faire le CRUD	00:20:00	00:24:00	00:00:00	1
Page majorer	CRUD	Faire le CRUD	00:30:00	00:33:00	00:00:00	1
Toutes pages	affichage	Configuration des autorisations	00:10:00	00:10:00	00:00:00	1
Page pointage	métier	insertion des pointages	00:10:00	00:28:00	00:00:00	1
Global	métier	add delete to all tables	00:10:00	00:00:00	00:10:00	0
Global	affichage	Mobile first	00:05:00	00:05:00	00:00:00	1
Page pointage	métier	exporter PDF Paie	00:35:00	00:41:00	00:00:00	1
Page pointage	affichage	changement affichage	00:10:00	00:10:00	00:00:00	1
Page pointage	métier	calculerHeure changement	00:20:00	00:30:00	00:00:00	1
Page paie	affichage	Fiche de paie	00:10:00	00:10:00	00:00:00	1
Page paie	métier	calculerPaie	00:30:00	00:35:00	00:00:00	1
Page statistiques	affichage	Employé avec montant total à payer	00:15:00	00:22:00	00:00:00	1
Page statistiques	contrôlleur	geStatistiques	00:05:00	00:05:00	00:00:00	1
Page statistiques	métier	Statistiques	00:20:00	00:27:00	00:00:00	1
Page statistiques	métier	Statistiques catégorie employé	00:20:00	01:30:00	00:00:00	1
Page insertion de heure	métier	check que nombre heures ≥ a et ≤ b	00:10:00	00:00:00	00:10:00	0
Page pointage	métier	Mise à jour pointage	00:20:00	00:30:00	0	1

		Total	11:15:00	16:21:00	00:20:00	0,98001998001998